## User Stories
User Stories
Theme | Priority | As the... | I want to be able to... | so I can...
CALENDAR | 1 | user | add events to a calendar | easily keep track of my schedule.
UI | 2 | user | have multiple calendar layouts(month/day/week) | simplify event organzation
APP | 1 | user | allow application to run in background | let alarms go off even when the app isn't open
ALARM | 1 | user | save alarms | be alerted at proper time
EVENTS | 1 | user | view a list of all events | manage events easily
ALARM | 1 | user | add/delete an alarm to an event | remember to go to the event
ALARM | 1 | user | view a list of all alarms | manage alarms easier
ALARM | 1 | user | modify/select existing alarm types/features | customize my alarms as I see fit
PUZZLE | 1 | user | add a puzzle to an alarm | be sure i wakeup
GPS | 3 | user | view GPS directions to event destination (option) | get where i'm going without an extra step of looking up directions
PUZZLE | 1 | user | choose from multiple puzzle types(logic, math...ect) | choose best option
GPS | 2 | user | add a gps location to an event | find where i need to go
UI | 3 | user | save my place in the application when i close it | easily take up where i left off
UI | 2 | user | load calendar view when app loads | better visual orginization
UI | 3 | user | view day at a glance when holding device portrait oriented, week at a glance when holding device landscape oriented | better visual orginization
ALARM | 2 | user | set a recurring alarm | be reminded of recurring events
UI | 2 | user | slide view when keyboard appears | see everything and nothing is obstructed by keyboard
EVENTS | 2 | user | set a recurring event | be reminded of recurring events such as classes
PUZZLE | 1 | user | ability to skip puzzle if too hard | prevents alarm from ringing forever
CLASS | 1 | developer | prepare for presentation | have something to present at the end of sprint
APP | 3 | user | have a widget that shows events for that day | always know what i have going on
APP | 3 | user | add a load screen when app launches | better visual effect
CALENDAR | 2 | user | view calendar events in chronological order | know when event i need to go to next
ALARM | 3 | user | add as many alarms as memory permits | add as many alarms as i want
APP | 3 | user | import an .ics file | use existing calendars
CALENDAR | 3 | user | color code my calendar events | easily recognize events and correspond colors with urgency / importance
APP | 3 | user | sync with google calendar | use existing calendars
APP | 3 | user | sync with shared google calendars | know see events from friends / work / organizations
APP | 3 | User | Sync with facebook events | Know what facebook events are coming up
Note on V1: User stories provide a high-level overview of product requirements.

## Product Backlog
Product Backlog
Theme | Item | Pts | Priority
CALENDAR | display the list of events in chronological order | 1 | 1
CALENDAR | create an interface to edit events | 1 | 1
CALENDAR | implement interface for event editing | 2 | 1
EVENTS | create an event data structure | 4 | 1
EVENTS | link event creation page to data structure | 2 | 1
EVENTS | create an interface to view/select events as a chronological list | 1 | 1
PUZZLE | add a puzzle to an alarm | 2 | 1
PUZZLE | have multiple puzzle options | 1 | 1
PUZZLE | be able to generate random puzzle of selected type | 2 | 1
PUZZLE | be able to skip a puzzle and regenerate a new one | 1 | 1
APP | allow application to run in the background | 1 | 1
ALARM | create an alarm data structure | 4 | 1
ALARM | add/delete an alarm or events | 1 | 1
ALARM | create an interface to view/select alarms as a list in the order in which they were created | 1 | 1
ALARM | create an interface to edit alarms | 1 | 1
ALARM | implement interface for alarm editing | 2 | 1
UI | open to the calendar view on starting the application | 1 | 2
UI | Portrait and Landscape views (need to make it able to choose views) Research! | 2 | 2
UI | enable scrollable screen when keyboard activates | 1 | 2
ALARM | have events and alarms that are recurring show on each of the days that they are occuring | 1 | 2
CALENDAR | have multiple calendar layouts | 1 | 2
CALENDAR | be able to set an event as recurring | 1 | 2
ALARM | be able to set an alarm as recurring | 1 | 2
GPS | associate and store a GPS location with an event | 4 | 3
UI | Change to day at a glance when in portrait orientation, week at a glance when in landscape | 1 | 3
GPS | integrate Google Maps API | 2 | 3
APP | implement a widget | 2 | 3
APP | have widget pull information and events from the application and display them on the screen | 2 | 3
APP | show a loading screen while the application is loading | 1 | 3
UI | Have the application save data and reload it when the app is relaunced | 1 | 3
APP | be able to read and pull the information from .ics files | 4 | 3
CALENDAR | be able to color code events | 1 | 3
APP | use the information from .ics file and store as events in the calendar | 2 | 3
APP | Link to facebook and import events | 4 | 3
APP | Link to google calendar events | 4 | 3
APP | Link to shared google calendars | 4 | 3
GPS | pull the current GPS location from the phone | 2 | 3
GPS | ensure that GPS location is activated | 2 | 3
GPS | use current location and event location to generate directions | 4 | 3
CALENDAR | calendar display which allows the user to click a day and add an event to that day | 2 | 1
CALENDAR | Data structure to sort dates(month/day/year) and contains instantiated events | 2 | 1
Note on A1: The Product Backlog is a project-level to do list, and a super-set of all Sprint Backlogs.

## Completed Items
Done (& Dropped) Items
Theme | Item | Remarks | Pts | Priority
Note on A1: The Product Backlog is a project-level to do list, and a super-set of all Sprint Backlogs.

## Sprint 1
Sprint 1 Backlog | [5 empty] | Date | 3/14 - 3/20 |  |  | 3/21 - 3/27 |  |  | 3/28 - 4/3
Backlog Item | Pts. | Priority | Owner | Status | Remarks | Day: | W | F | M | W | F | M | W | F | M
create an event data structure | 4 | 1 | Alex | done |  |  | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 0
link event creation page to data structure | 2 | 1 | Alex | done |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
create an alarm data structure | 4 | 1 | Alex | done |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 0
create an interface to view/select events as a chronological list | 1 | 1 | Ainsworth | parked | same as 16 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
add/delete an alarm or events | 1 | 1 | Alex | done |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
create an interface to view/select alarms as a list in the order in which they were created | 1 | 1 | Ainsworth | parked |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
create an interface to edit alarms | 1 | 1 | Mayra | done |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
implement interface for alarm editing | 2 | 1 | Mayra/Alex | done |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
add a puzzle to an alarm | 2 | 1 | Kevin | blocked | Need AlarmManager functionality |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1
have multiple puzzle options | 1 | 1 | Kevin | done |  |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
be able to skip a puzzle and regenerate a new one | 1 | 1 | Kevin | done |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
be able to generate random puzzle of selected type | 2 | 2 | Adam | parked |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1
allow application to run in the background | 1 | 1 | Adam | done | Researched, Android does this, but autokills some processes if memory gets too low. |  | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0
display the list of events in chronological order | 1 | 2 | Cameron | blocked | Requires switching between entire Calendar view and list of events view |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
have multiple calendar layouts | 1 | 2 | Michael | parked |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4
open to the calendar view on starting the application | 1 | 3 | Adam | done |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
be able to set an alarm as recurring | 1 | 2 | Victoria | done |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
have events and alarms that are recurring show on each of the days that they are occuring | 1 | 2 | Ainsworth | blocked | Calendar |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
be able to set an event as recurring | 1 | 2 | Victoria | parked |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
enable scrollable screen when keyboard activates | 1 | 2 | Mayra | done |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
be able to read and pull the information from .ics files | 4 | 3 | ? | parked |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
use the information from .ics file and store as events in the calendar | 2 | 3 | ? | parked |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
create an interface to edit events | 1 | 1 | Mayra | done |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
implement interface for event editing | 2 | 1 | Mayra | done |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
calendar display which allows the user to click a day and add an event to that day | 2 | 1 | Michael | done |  |  | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 0
Data structure to sort dates(month/day/year) and contains instantiated events | 2 | 1 | Michael | parked |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
Note on C2: Based on complexity. Initial estimate should follow: exponential (1,2,4,8,...) OR fibonacci (1,2,3,5,8,...)
Note on AP2: Who gets choked if this item doesn't get done?
Note on AT2: Done? Blocked? Choose an item from the drop-down menu.
Note on AU2: How important is this?

## Sprint 1 Burndown
Sprint 1 Burndown Chart
Date | 3/14 - 3/20 |  |  | 3/21 - 3/27 |  |  | 3/28 - 4/3
Day | W | F | M | W | F | M | W | F | M
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Actual | 37 | 37 | 37 | 37 | 37 | 35 | 33.5 | 30.5 | 15
Ideal | 39 | 32.375 | 27.75 | 23.125 | 18.5 | 13.875 | 9.25 | 4.625 | 0

## Sprint 2
[6 empty] | Date | 4/4 - 4/10 |  |  | 4/11 - 4/17 |  |  | 4/18 - 4/24
Backlog Item | Pts. | Priority | Owner | Status | Remarks | Day: | W | F | M | W | F | M | W | F | M
create an interface to view/select events as a chronological list | 2 | 1 | Mayra & Michael | in progress | Page is created, Michael is figuring out how to add the events |  | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1
create an interface to view/select alarms as a list in the order in which they were created | 1 | 1 | Kevin | done | done for the current state of alarms. Alarms do not currently save data outside of time and name i believe |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
add a puzzle to an alarm | 1 | 1 | Alex | done |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
be able to generate random puzzle of selected type | 1 | 2 | Kevin | done |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
display the list of events in chronological order | 1 | 2 | Michael | in progress |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
have multiple calendar layouts | 1 | 2 | Michael | in progress |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
have alarms that are recurring show on each of the days that they are occuring | 1 | 2 | Victoria | done |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
be able to set an event as recurring | 1 | 2 | Victoria | done |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
be able to read and pull the information from .ics files | 4 | 3 | Cameron & Ainsworth | in progress |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
use the information from .ics file and store as events in the calendar | 2 | 3 | Kevin & Mayra | Blocked |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Data structure to sort dates(month/day/year) and contains instantiated events | 2 | 1 | Alex | done |  |  | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
change to day at a glance when in portrait orientation, week at a glance in landscape | 1 | 3 | Michael | in progress |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
integrate Google Maps API | 2 | 3 | robin | done |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
implement a widget | 2 | 3 | adam | in progress | Researched widgets |  | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1
have widget pull information and events from the application and display them on the screen | 2 | 3 | adam | in progress |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
show a loading screen while the application is loading | 1 | 3 | adam | in progress |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Have the application save data and reload it when the app is relaunced | 1 | 3 | Alex & Mayra | in progress | Researching and then implementing |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
be able to color code events | 1 | 3 | Mayra | parked | Researching |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Create a database of puzzle for alarms | 2 | 1 | Victoria | done |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Link to google calendar events | 4 | 3 | robin & ainsworth | parked |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Link to shared google calendars | 2 | 3 | robin | parked |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
pull the current location and event location to generate directions | 2 | 3 | robin | done |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
calendar display which allows the user to click a day and add an event to that day and show how many events are in a day from the calendar | 2 | 1 | Michael | in progress |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1
Get AlarmManager functionality to open puzzle Activities | 2 | 1 | Alex | done |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
Get sounds to play for alarms | 4 | 1 | Mayra | done |  |  | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 1 | 1
Add sounds to emulator | 1 | 1 | Robin | done |  |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Add new empty page before add events page | 1 | 1 | Mayra | done |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Note on B2: Based on complexity. Initial estimate should follow: exponential (1,2,4,8,...) OR fibonacci (1,2,3,5,8,...)
Note on C2: How important is this?
Note on D2: Who gets choked if this item doesn't get done?
Note on E2: Done? Blocked? Choose an item from the drop-down menu.

## Sprint 2 Burndown
Sprint 2 Burndown Chart
Date | 4/4-4/10 |  |  | 4/11-4/17 |  |  | 4/18-4/23
Day | W | F | M | W | F | M | W | F | M
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Actual | 46 | 45 | 45 | 43 | 41 | 40 | 36 | 28 | 26
Ideal | 47 | 41.125 | 35.25 | 29.375 | 23.5 | 17.625 | 11.75 | 5.875 | 0

## Action Items
Action Items
Description | Owner(s) | Urgency | Status | Remarks
Note on A1: A working list of miscellaneous items to be completed.
Note on C2: Choose an item from the drop-down menu.
Note on D2: Choose an item from the drop-down menu.