## User Stories
User Stories
Theme | Priority | As the... | I want to be able to... | so I can...
calendar | Medium | user | import my calendar | view and manage events visually on a calendar
countdown | Low | user | see the countdown to the event | see in real time when it is about to start
DB | High | developer | save the account info | manages the users in DB
DB | High | developer | save the event info | manages the events in DB
events | High | user | view events according to categories or sub-categories | view them in orderly fashion
events | High | user | withdraw from events | manage my events
events | High | organizer | post events | submit events that are coming up
events | High | organizer | edit/delete events | make any changes to the information posted previously
events | High | organizer | view events | manage the events posted by me
favorite | High | user | add favorite categories | view events according to my favorite category
favorite | High | user | delete favorite categories | set my preferences
feedback | Low | user | give feedback for the events | help the organizers with all positives and negatives of the events
feedback | Low | organizer | see the feedback posted by users | improve services and facilities for future events
location | Low | user | know the location of event | see the location of event on Google Maps and navigate
newsfeed | High | user | see news feed of events | see latest events
notification | High | user | be appropriately notified about events | be aware of any changes to my events schedule
notification | Medium | user | view missed notification | view all notifications
notifications | medium | developer | setup push notifications | update user about changes to their events / send reminders
participants | Low | organizer | see participants list | gauge response for my events to invite people for future events or references
participants | High | organizer | see participants count | gauge response for my events
Registration | High | user | Register/Login | save my Profile
Registration | High | organizer | Register/Login | save my Profile
Responsive Design | Low | organizer | access Web Application over phone or tablets | post/edit/delete events on the go
RSVP | High | user | RSVP events | see all events I want to go in one place
search | High | user | search for events | quickly find events
Server Connection | High | developer | set and connect to server | operate DB and save data to DB
social | Low | user | share my events on Social Media | let my friends know about the event
social | Low | user | invite my friends to an event using Facebook | have my friends accompanying me to the event
SQL | High | developer | sync SQL and SQLite | update the user about the latest events
tokens | High | developer | create authorization token | create user sessions for the android app
Note on V1: User stories provide a high-level overview of product requirements.

## Product Backlog
Product Backlog
Theme | Item | Pts | Priority | Sprint No.
Accounts | Save users and organizers personal information | 4 | High | 1
Accounts | Edit users' favorite categories in database | 4 | High | 1
Android UI | Implement all UI pages of the Android application | 40 | High | 1
Android UI | Implement viewing events news feed on Android application | 8 | High | 1
Android UI | Implement the functionality of viewing events by specific category on Android application | 16 | High | 1
Android UI | Add/delete favorite categories by user on Android application | 20 | High | 1
Android UI | Implement the swipe navigation for categories | 20 | High | 1
Android UI | Implement events RSVP by swiping events shown on Android events page | 0 | Med | Dropped
Android UI | Create count for events | 50 | Low | 2
Android UI | Share events that a user planning to attend on Facebook | 40 | Low | 3
Android UI | Invite friends on Facebook to events | 50 | Low | 2
App | Sending notifications of up coming events to users who signed in | 0 | Med | Dropped
Calendar | Build calendar interface on Android app and web | 24 | Low | 3
DB | Create tables | 20 | High | 1
DB/Web UI | Count attendees for a specific event and display the number to organizers | 8 | Med | 3
Events | Implement the functionality of posting events by organizers to database | 12 | High | 1
Events | Implement functionality of edit/delete events from database | 8 | High | 1
Events | Create my events tags on Android applications | 4 | High | 1
GPS | Add locations based navigation for a chosen events | 0 | Low | Dropped
Registration | Implement register/login in functionalities of Android application | 8 | High | 1
Search | Extensile seach field | 40 | Med | 2
Search | Implement date-based search | 60 | Low | 3
Server | Set a server | 4 | High | 1
Web UI | Implement all UI pages of the web version of the application | 24 | High | 1
Web UI | Implement register/login in functionalities for the Web version | 8 | High | 1
Web UI | Implement category tags for organizers on web | 16 | High | 1
Web UI | Implement the responsive design of the web version | 16 | Low | 2
Web UI | Display attendees for a specific events as a list | 0 | Low | Dropped
Web UI | Display all events that posted | 8 | High | 1
Web UI | View user feedbacks after an event | 0 | Low | Dropped
Total Hours |  | 512
Note on S1: User stories provide a high-level overview of product requirements.

## Sprint 2
Sprint 2 Backlog
Backlog Item | Pts. | Priority | Owner | Status | Remarks | Date: | 10/14 - 10/19 |  |  | 10/21 - 10/26 |  |  | 10/28 - 11/2 |  |  | 11/4 - 11/9
[6 empty] | Day: | Wed | Fri | Mon | Wed | Fri | Mon | Wed | Fri | Mon | Wed | Fri | Mon
Implement all UI pages of the web version of the application | 2 | High | Jiayong, Chang | done |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implement register/login in functionalities of Android application | 5 | High | Vineet | done | connection |  | 5 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implement functionality of edit/delete events from database | 4 | High | Shubham, Gagan, Zhaohe | done |  |  | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implement viewing events news feed on Android application | 3 | High | Vineet, Zhaohe | done |  |  | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implement category tags for organizers on web | 12 | High | Jiayong, Chang | done |  |  | 12 | 8 | 5 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0
Implement the functionality of viewing events by specific category on Android application | 7 | High | Vineet, Shubham | done | wait for events data |  | 7 | 5 | 4 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Add/delete favorite categories by user on Android application | 10 | High | Zhaohe | done | redisign table relation |  | 10 | 10 | 10 | 10 | 10 | 9 | 4 | 0 | 0 | 0 | 0 | 0
Edit users' favorite categories in database | 4 | High | Vineet | done | redisign table relation |  | 4 | 4 | 4 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Display all events that posted | 2 | High | Shubham, Zhaohe | done |  |  | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Extensile seach field | 40 | Med | Vineet, Zhaohe,Shubham | done |  |  | 40 | 35 | 32 | 25 | 25 | 21 | 18 | 18 | 15 | 12 | 0 | 0
Create count for events | 50 | Low | Gagan, Shubham, Jiayong | done |  |  | 50 | 46 | 42 | 37 | 33 | 28 | 26 | 23 | 21 | 18 | 8 | 0
Implement the responsive design of the web version | 16 | Low | Chang, Shubham | done |  |  | 16 | 16 | 16 | 16 | 16 | 13 | 11 | 7 | 3 | 0 | 0 | 0
Display attendees for a specific events as a list | 0 | Low | Zhaohe,Shubham | dropped |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implement date-based search | 60 | Low | Zhaohe, Jiayong,Gagan | done |  |  | 60 | 54 | 46 | 38 | 31 | 26 | 26 | 24 | 22 | 16 | 11 | 0
Total Hours left after each Meeting: | [6 empty] | 215 | 191 | 168 | 142 | 126 | 100 | 87 | 72 | 61 | 46 | 19 | 0
Total Sprint-2 Hours | 215
[7 empty] | 215 | 191 | 168 | 142 | 126 | 100 | 87 | 72 | 61 | 46 | 19 | 0
Note on W1: User stories provide a high-level overview of product requirements.

## Sprint 2 Burndown
Sprint 2 Burndown Chart
Date: | 10/14 - 10/19 |  |  | 10/21 - 10/26 |  |  | 10/28 - 11/2 |  |  | 11/4 - 11/9
Day: | Wed | Fri | Mon | Wed | Fri | Mon | Wed | Fri | Mon | Wed | Fri | Mon
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Actual | 215 | 191 | 168 | 142 | 126 | 100 | 87 | 72 | 61 | 46 | 19 | 0
Ideal | 215 | 195.4545 | 175.9091 | 156.3636 | 136.8182 | 117.2727 | 97.7273 | 78.1818 | 58.6364 | 39.0909 | 19.5455 | 0
Work Done | 0 | 24 | 23 | 26 | 16 | 26 | 13 | 15 | 11 | 15 | 27 | 19

## Sprint 3
Share events that a user planning to attend on Facebook | 40
Build calendar interface on Android app and web | 24
Count attendees for a specific event and display the number to organizers | 8
Invite friends on Facebook to events | 50
122

## Sprint 1
Sprint 1 Backlog
Backlog Item | Pts. | Priority | Owner | Status | Remarks | Date: | 9/23 - 9/28 |  |  | 9/30 - 10/05 |  |  | 10/07 - 10/12
[6 empty] | Day: | Wed | Fri | Mon | Wed | Fri | Mon | Wed | Fri | Mon
Implement all UI pages of the Android application | 40 | High | Zhaohe, Vineet, Shubham | done | Home page, icon |  | 40 | 34 | 22 | 15 | 12 | 8 | 5 | 3 | 0
Implement all UI pages of the web version of the application | 24 | High | Jiayong, Chang | done | Almost done |  | 24 | 22 | 19 | 15 | 12 | 8 | 5 | 2 | 2
Implement register/login in functionalities of Android application | 8 | High | Vineet | done | connection |  | 8 | 7 | 6 | 6 | 6 | 6 | 5 | 5 | 5
Implement login register functionalities for the Web version | 8 | High | Chang, Jiayong | done |  |  | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 0
Set a server | 4 | High | Gagan | done |  |  | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0
Save users and organizers personal information | 4 | High | Shubham, Gagan | done |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
Implement the functionality of posting events by organizers to database | 12 | High | Jiayong, Chang | done |  |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 6 | 0
Implement functionality of edit/delete events from database | 8 | High | Shubham, Gagan, Zhaohe | done |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4
Implement viewing events news feed on Android application | 8 | High | Vineet, Zhaohe | done |  |  | 8 | 7 | 6 | 6 | 6 | 6 | 5 | 5 | 3
Implement category tags for organizers on web | 16 | High | Jiayong, Chang | done |  |  | 16 | 16 | 16 | 16 | 16 | 16 | 12 | 12 | 12
Implement the functionality of viewing events by specific category on Android application | 16 | High | Vineet, Shubham | done | wait for events data |  | 16 | 16 | 16 | 16 | 16 | 13 | 11 | 10 | 7
Add/delete favorite categories by user on Android application | 20 | High | Zhaohe | done |  |  | 20 | 19 | 16 | 15 | 11 | 10 | 10 | 10 | 10
Edit users' favorite categories in database | 4 | High | Vineet | done |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Create my events tags on Android applications | 4 | High | Shubham | done |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 0
Implement the swipe navigation for categories | 20 | High | Zhaohe, Vineet | done |  |  | 20 | 19 | 16 | 15 | 12 | 12 | 11 | 6 | 0
Display all events that posted | 8 | High | Shubham, Zhaohe | done | just a demo |  | 8 | 8 | 8 | 8 | 7 | 6 | 4 | 2 | 2
Create tables | 20 | High | Shubham, Gagan | done |  |  | 20 | 18 | 11 | 7 | 2 | 0 | 0 | 0 | 0
Total Hours | 224
Note on T1: User stories provide a high-level overview of product requirements.

## Sprint 1 Burndown
Sprint 1 Burndown Chart
Date: | 9/23 - 9/28 |  |  | 9/30 - 10/05 |  |  | 10/07 - 10/12
Day: | Wed | Fri | Mon | Wed | Fri | Mon | Wed | Fri | Mon
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Actual | 224 | 206 | 176 | 157 | 136 | 121 | 104 | 81 | 49
Ideal | 224 | 196 | 168 | 140 | 112 | 84 | 56 | 28 | 0

## Completed Items
Done (& Dropped) Items
Theme | Item | Remarks | Pts | Priority
Android UI | Implement all UI pages of the Android application
Web UI | Implement login register functionalities for the Web version
Server | Set a server
Accounts | Save users and organizers personal information
Events | Implement the functionality of posting events by organizers to database
Events | Create my events tags on Android applications
Android UI | Implement the swipe navigation for categories
DB | Create tables
Web UI | Implement all UI pages of the web version of the application
Events | Implement functionality of edit/delete events from database
Note on A1: The Product Backlog is a project-level to do list, and a super-set of all Sprint Backlogs.

## Action Items
Action Items
Description | Owner(s) | Urgency | Status | Remarks
Note on A1: A working list of miscellaneous items to be completed.
Note on C2: Choose an item from the drop-down menu.
Note on D2: Choose an item from the drop-down menu.