## User Stories
User Stories
Theme | Priority | As the... | I want to be able to... | so I can...
Registration | High | user | Register/Login | save my Profile
favorite | High | user | add favorite categories | view events according to my favorite category
favorite | High | user | delete favorite categories | set my preferences
events | High | user | view events according to categories or sub-categories | view them in orderly fashion
newsfeed | High | user | see news feed of events | see latest events
RSVP | High | user | RSVP events | see all events I want to go in one place
events | High | user | withdraw from events | manage my events
notification | High | user | be appropriately notified about events | be aware of any changes to my events schedule
search | High | user | search for events | quickly find events
calendar | Medium | user | import my calendar | view and manage events visually on a calendar
notification | Medium | user | view missed notification | view all notifications
location | Low | user | know the location of event | see the location of event on Google Maps and navigate
Registration | High | organizer | Register/Login | save my Profile
events | High | organizer | post events | submit events that are coming up
events | High | organizer | edit/delete events | make any changes to the information posted previously
events | High | organizer | view events | manage the events posted by me
participants | Low | organizer | see participants list | gauge response for my events to invite people for future events or references
participants | High | organizer | see participants count | gauge response for my events
Responsive Design | Low | organizer | access Web Application over phone or tablets | post/edit/delete events on the go
Server Connection | High | developer | set and connect to server | operate DB and save data to DB
SQL | High | developer | sync SQL and SQLite | update the user about the latest events
DB | High | developer | save the account info | manages the users in DB
DB | High | developer | save the event info | manages the events in DB
notifications | medium | developer | setup push notifications | update user about changes to their events / send reminders
tokens | High | developer | create authorization token | create user sessions for the android app
countdown | Low | user | see the countdown to the event | see in real time when it is about to start
social | Low | user | share my events on Social Media | let my friends know about the event
social | Low | user | invite my friends to an event using Facebook | have my friends accompanying me to the event
feedback | Low | user | give feedback for the events | help the organizers with all positives and negatives of the events
feedback | Low | organizer | see the feedback posted by users | improve services and facilities for future events
Note on V1: User stories provide a high-level overview of product requirements.

## Product Backlog
Product Backlog
Theme | Item | Pts | Priority
Android UI | Implement all UI pages of the Android application | 20 | High
Web UI | Implement all UI pages of the web version of the application | 12 | High
Registration | Implement register/login in functionalities of Android application | 4 | High
Web UI | Implement register/login in functionalities for the Web version | 4 | High
Server | Set a server | 2 | High
Accounts | Save users and organizers personal information | 2 | High
Events | Implement the functionality of posting events by organizers to database | 6 | High
Events | Implement functionality of edit/delete events from database | 4 | High
Android UI | Implement viewing events news feed on Android application | 4 | High
Web UI | Implement category tags for organizers on web | 8 | High
Android UI | Implement the functionality of viewing events by specific category on Android application | 8 | High
Android UI | Add/delete favorite categories by user on Android application | 10 | High
Accounts | Edit users' favorite categories in database | 2 | High
Events | Create my events tags on Android applications | 2 | High
Search | Implement the text-based search | 20 | Med
Search | Implement date-based search | 20 | Low
Calendar | Build calendar interface on Android app and web | 12 | Low
App | Sending notifications of up coming events to users who signed in | 12 | Med
Android UI | Implement the swipe navigation for categories | 10 | High
Web UI | Implement the responsive design of the web version | 8 | Low
Web UI | Display attendees for a specific events as a list | 8 | Low
Web UI | Display all events that posted | 4 | High
Android UI | Implement events RSVP by swiping events shown on Android events page | 8 | Med
DB/Web UI | Count attendees for a specific event and display the number to organizers | 4 | Med
DB | Create tables | 10 | High
Android UI | Create countdown for events | 16 | Low
GPS | Add locations based navigation for a chosen events | 12 | Low
Android UI | Share events that a user planning to attend on Facebook | 12 | Low
Android UI | Invite friends on Facebook to events | 20 | Low
Web UI | View user feedbacks after an event | 10 | Low
Total Hours |  | 274
Note on T1: User stories provide a high-level overview of product requirements.

## Completed Items
Done (& Dropped) Items
Theme | Item | Remarks | Pts | Priority
Note on A1: The Product Backlog is a project-level to do list, and a super-set of all Sprint Backlogs.

## Sprint 1
Sprint 1 Backlog
Backlog Item | Pts. | Priority | Owner | Status | Remarks | Date: | 9/23 - 9/28 |  |  | 9/30 - 10/05 |  |  | 10/07 - 10/12
[6 empty] | Day: | Wed | Fri | Mon | Wed | Fri | Mon | Wed | Fri | Mon
Implement all UI pages of the Android application | 20 | High | Zhaohe, Vineet, Shubham | to do |  |  | 10
Implement all UI pages of the web version of the application | 12 | High | Jiayong, Chang | to do |  |  | 6
Implement register/login in functionalities of Android application | 4 | High | Vineet | to do |  |  | 2
Implement login register functionalities for the Web version | 4 | High | Chang, Jiayong | to do |  |  | 2
Set a server | 2 | High | Gagan | done |  |  | 1
Save users and organizers personal information | 2 | High | Shubham, Gagan | to do |  |  | 1
Implement the functionality of posting events by organizers to database | 6 | High | Jiayong, Chang | to do |  |  | 3
Implement functionality of edit/delete events from database | 4 | High | Shubham, Gagan, Zhaohe | to do |  |  | 2
Implement viewing events news feed on Android application | 4 | High | Vineet, Zhaohe | to do |  |  | 2
Implement category tags for organizers on web | 8 | High | Jiayong, Chang | to do |  |  | 4
Implement the functionality of viewing events by specific category on Android application | 8 | High | Vineet, Shubham | to do |  |  | 4
Add/delete favorite categories by user on Android application | 10 | High | Zhaohe | to do |  |  | 5
Edit users' favorite categories in database | 2 | High | Vineet | to do |  |  | 1
Create my events tags on Android applications | 2 | High | Shubham | to do |  |  | 1
Implement the swipe navigation for categories | 10 | High | Zhaohe, Vineet | to do |  |  | 5
Display all events that posted | 4 | High | Shubham, Zhaohe | to do |  |  | 2
Create tables | 10 | High | Shubham, Gagan | to do |  |  | 5
Total Hours | 112
Note on T1: User stories provide a high-level overview of product requirements.

## Sprint 1 Burndown
Sprint 1 Burndown Chart
Date | 9/18 - 9/28 |  |  | 9/29 - 10/8 |  |  | 10/8 - 10/18
Day | W | F | M | W | F | M | W | F | M
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Actual | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal | 112 | 98 | 84 | 70 | 56 | 42 | 28 | 14 | 0

## Action Items
Action Items
Description | Owner(s) | Urgency | Status | Remarks
Note on A1: A working list of miscellaneous items to be completed.
Note on C2: Choose an item from the drop-down menu.
Note on D2: Choose an item from the drop-down menu.